# Oakwood University AI Studio + Engineering Lab — IDC Proposal & Invoice

Island Dev Crew Consulting · General Contracting & AI Systems

# Oakwood University AI Studio
& Engineering Lab

Turnkey proposal & execute-ready estimate for a 10-seat AI production studio, a hands-on engineering/soldering makerspace, and the department-wide power, network, camera, and access-control infrastructure that protects the investment — orchestrated end-to-end by Island Development Crew.

Prepared: June 2026
Client: Dr. Shushannah Smith
Chair, Mathematics & Computer Science
Oakwood University · Cooper Complex Bldg B
Huntsville, AL · ssmith@oakwood.edu
Provider: Jonathan Isaac
Island Development Crew LLC
256-668-8248 · jon-isaac@islanddevcrew.com

What this is. A planning-grade, audit-aware General-Contractor proposal built from an on-site walkthrough (May 26, 2026), 71 verified site photographs, and current June-2026 vendor pricing with named Huntsville subcontractors. IDC orchestrates every trade under one accountable point of contact, one transparent fee, and one progress dashboard. Figures are planning ranges; each line is re-quoted to a sealed vendor/sub bid before purchase.

10-Seat AI Studio · Rm 409Soldering/Math Lab · Rm 407Engineering · Rm 305 + 310UniFi + pfSense NetworkUniFi Protect CamerasMulti-Door Access≥4 Bambu Lab Printers2084 / Lennox Curriculum

Recommended Execution — All-In (IDC-Orchestrated)

$172,000

Range $170,625 – $198,498. Includes equipment, subbed facility work, GC coordination, contingency, and the 10% IDC orchestration fee. Title III grant-eligible portion ≈ $93.5K; facility/capital portion ≈ $60.1K.

Mobilization deposit $68,000 initiates procurement & sub scheduling (see Payment Schedule, p.8).

Secure payment: Island Dev Crew Stripe payment link ($68,000 mobilization deposit)

Signing: signature-ready PDF with direct blocks (p.8); DocuSign / SignWell / Dropbox Sign accepted.

Department-Wide Vision (full robust build incl. dept cabling, dept cameras, Room-405 bathroom & raised floor) is on p.11 as the donor / naming-gift envelope at $245K–$330K.

### The opportunity

Oakwood does not need another computer lab. It needs an AI production studio where Math & Computer Science students ship AI — apps, agents, fabricated hardware, and research artifacts — backed by reliable power, network, and security. As the only Seventh-day Adventist HBCU, Oakwood can also give students a credible responsible-AI ethics voice (curriculum, p.9).

### Why IDC as GC

One orchestrator manages every vendor and Huntsville subcontractor (electrical, low-voltage, access, GC), holds a single 3–7% coordination markup on subbed facility work and a transparent 10% orchestration fee, and keeps faculty & administration informed through a live progress dashboard with weekly/monthly reports.

Island Dev Crew Consulting · jon-isaac@islanddevcrew.comOakwood AI Lab Proposal · Page 1 of 13

## 1 · Executive Summary & How to Read This

This package separates the project into the three quote families requested, because each draws on different funding. Selling all three as one grant line will be clawed back at audit.

| Track | Scope | Planning range | Funding lane |
| --- | --- | --- | --- |
| Quote 1 — AI Studio + Engineering | Compute, Bambu fleet, soldering/CNC, AV + 3 boards, furniture, consumables, software | $88.2K–$98.8K | Mostly Title III grant-eligible |
| Quote 2 — Power / Electrical | FPE panel replacement, subpanel, dedicated circuits, raceway, raised floor, permits | $54.4K–$61.0K | Facility — NOT grant (capital / donor) |
| Quote 3 — Network + Cameras + Access | UniFi + pfSense, Protect cameras, 4-door Access; + structured cabling labor | Equip grant; cabling facility | Mixed |

## 2 · Two Tiers — Recommended vs. Vision

### Recommended Execution — ~$172,000 all-in

Studio/lean compute, lab-focused facility scope (power + cabling to the labs + MDF; raised floor in the AI Studio only; no Room-405 bathroom). The number to commit to — top of the $150–175K band you targeted; the execute-ready invoice (p.8) bills this.

### Department-Wide Vision — $245K–$330K

Full robust transformation: pooled compute (RTX PRO 6000), dept-wide cabling (80 drops + fiber), dept-wide cameras, full electrical, raised floor plus the Room-405 bathroom and dept room-mod, 5-door access. The donor / naming-gift envelope (p.11).

## 3 · The Funding Firewall (critical)

Title III covers supplies (<$2,000/unit) and equipment (≥$2,000/unit) tied to the academic mission, with an audit trail and a June 30 spend pressure. It does not cover facilities — electrical service, structural cabling labor, raised floor, construction, HVAC, the bathroom. Quote 2 in full and the cabling-labor / door-install portions of Quote 3 must come from capital, physical-plant, donor, or match funds.

## 4 · Sequencing — two hard dependencies + 90-day plan

- No compute energizes before Quote 2 circuits. The RTX workstation (575–600W) and DGX nodes need the dedicated 20A/30A circuits first.

- The studio is unusable before Quote 3 drops. Room 409 currently has one data drop; the 10GbE backbone + new drops come before deployment.

| Phase | Actions |
| --- | --- |
| Now → June 30 | Lock education-priced POs for Quote 1 (quotes expire 14–30 days); commission the licensed-electrician load study; campus-IT vendor ruling; confirm tax-exempt + line-by-line grant eligibility. |
| 30 days | Sealed sub bids (3 each: electrical, low-voltage, access, GC); permits; cabling + raised-floor design; finalize room dimensions & seat count. |
| 90 days | Install power → cabling/network → compute → cameras/access → demo day. Display boards + dashboard go live; first cohort onboards. |

Island Dev Crew Consulting · jon-isaac@islanddevcrew.comOakwood AI Lab Proposal · Page 2 of 13

## 5 · Existing-Conditions Assessment (Walkthrough, May 26 2026)

A true on-site assessment was performed with Dr. Smith and is documented by all 71 verified photographs (16 isolated as exhibits on pp.4–5; the full set with explanations is on the online resource page). Room → lab mapping:

| Room | Becomes | Condition found (drives scope) |
| --- | --- | --- |
| 409 | AI Studio (10–13 seats) | Preferred room. One data drop; breakers trip on space heaters; keep dual smartboards (one Wacom) + 2 projectors; fire-egress concern; surface-run power on bare block. |
| 407 | Math & Soldering Lab | Convertible; blue steel pegboard workbenches + empty cabinetry + lab sink (reusable); an "L-bend" fits a fume extractor. |
| 305 + 310 | Engineering Lab | 305 = project room (benches, existing MakerBot 3D printers). 310 = computer lab with rows of tower desktops (NVIDIA-GPU) to repurpose for AI hosting — saves the engineering budget. |
| MDF closet | Network core + power | Federal Pacific (FPE) panelboard "2C" with exposed bus + mixed 15/20/25/30A breakers, co-located with the network patch/fiber field (not to code); drops out ~monthly. |

⚠ Priority safety finding: the MDF closet contains a Federal Pacific Electric (FPE) panel (EX-01–03) — a panel type with a documented industry history of breakers failing to trip on overload, a recognized fire hazard. Replacing it is strongly recommended and is carried in Quote 2. Whole-complex: no 90° angles, 15 "Frankensteined" AC units, windows with failed glazing/interpane fogging, bare cinderblock.

### In Dr. Smith's words

"I've only got the one data drop right there." — (asked: in the entire room?) — "Yes, that's it right there."

"These electrical units, they can't handle nothing… I got portable heaters… Boom." → "That means your breakers need to be updated."

"I know this is not to code. We're not supposed to have a closet next to the fuse box."

"The main objective: secure and always changing… nobody could copy it or retain that information." (access control)

"We want AI. We need power. Power is the number one thing you invest in."

Island Dev Crew Consulting · jon-isaac@islanddevcrew.comOakwood AI Lab Proposal · Page 3 of 13

## 6 · Photo Exhibit Addendum — Part 1 of 2 (verified on-site)

Each photograph was individually reviewed; captions describe what is actually in frame. All 71 walkthrough photographs are included at full resolution with explanations on the online resource page: resources.html.

EX-01 · power · MDF/networking closet: FPE panelboard 2C directory card, handwritten, showing circuits dominated by AC/heat and lighting loads for the 400-series rooms and hallways (incl. Rm 404-405, 409, 420)

EX-02 · power · MDF/networking closet: Interior of FPE panel 2C with deadfront off: exposed bus bars and a mix of 15/20/25/30A single- and double-pole breakers hand-labeled to rooms 405, 409, 420 and hallway/A

EX-03 · power · MDF/networking closet: Sharp close-up of the FPE panel directory enumerating receptacle, plug-mold, dedicated-outlet, lab-table, fire-alarm, and '3D'-printer circuits across Rooms 404-420, with

EX-04 · data-network · Hallway / classroom wall: Abandoned/exposed low-voltage drop: a surface-mount junction box with a loose twisted-pair (blue/yellow) hanging free and tucked behind the baseboard, not terminated in a

EX-05 · data-network · MDF/networking closet: MDF closet overview: a wall patch field and fiber breakout panel buried under unmanaged blue/gray/orange cabling routed through an open ceiling-tile gap, mounted on a bar

EX-06 · data-network · MDF/networking closet: Detail of the closet fiber distribution panel (rows A/B/C with red/blue couplers and yellow jumpers) beside a fiber-optic caution label and lone wall outlet, all on bare

EX-07 · AV · Classroom (AI Studio candidate: Primary AV wall: large interactive flat-panel display on an articulating mount, a soundbar above it, and a markerboard alongside, with exposed cabling and a wall-mounted

EX-08 · AV · 409: Mobile computer cart labeled for Math & Computer Science tethered by a single USB cable to a wall box, beside a wall-mounted flat panel with loose cabling. Shows reliance

Island Dev Crew Consulting · jon-isaac@islanddevcrew.comOakwood AI Lab Proposal · Page 4 of 13

## 7 · Photo Exhibit Addendum — Part 2 of 2

EX-09 · AV · Room 407 (Math & Soldering lab: Room 407 overview: rows of blue pegboard workbenches and stools beneath a recessed ceiling cassette AC unit and a ceiling-mounted projector, with two wall-mounted glass w

EX-10 · window · Classroom / exterior window: Window head/jamb corner showing chalky deposit and streaking at the glazing perimeter where the seal meets the frame. Documents the window-reseal need and moisture/efflor

EX-11 · window · Unspecified classroom/lab (dep: Window head detail showing failed glazing: pronounced interpane fogging across roughly half the pane and a marginal top seal against bare cinderblock, documenting the win

EX-12 · window · 409: Louvered wall grille over a window opening with bowed, misaligned blades and daylight leaking through gaps. Documents a damaged/ill-fitting louver assembly and a fenestra

EX-13 · bench · 407: Room 407 lab casework: continuous black-topped bench with stainless sink, faucet, and wood cabinetry. Only a single surface-mounted countertop duplex receptacle serves th

EX-14 · bench · Room 407 (Math & Soldering lab: Detail of Room 407 workbench assets: heavy blue steel benches with pegboard backboards, lower storage shelves, and matching wheeled stools. Clean documentation of reusabl

EX-15 · printer · Rooms 305/310 (Engineering): Crisp close-up of the engineering 3D printers, clearly identifying the MakerBot Replicator and a second enclosed unit. Best documentation of the existing 3D-printer asset

EX-16 · printer · Engineering computer lab (Room: Wide view of a fully equipped computer classroom: rows of tower desktops with dual flat-panel monitors on shared desks, blue task chairs throughout. Strong asset exhibit

These 16 are the strongest exhibits; the complete set of all 71 walkthrough photographs — with room/condition explanations — is on the online resource & references page.

Island Dev Crew Consulting · jon-isaac@islanddevcrew.comOakwood AI Lab Proposal · Page 5 of 13

## 8 · Quote 1 — AI Studio + Engineering Lab (Title III grant-eligible)

### AI Studio · Rm 409

10–13 high-memory seats so students run local models: 6× Framework Desktop 128GB (~$2,851) + 4× Mac Studio M4 Max 64GB (~$2,600) + 1× DGX Spark ($4,699) + an RTX 5090 workstation + Jetson AGX Thor + Orin Nano kits + Synology NAS + rack UPS + an 85″ demo wall. Keep the dual smartboards/2 projectors.

### Math & Soldering · Rm 407

5–10× Hakko FX-888DX soldering stations + recirculating BOFA 3D PrintPRO-class fume/VOC extraction in the cabinetry/L-bend; bench instruments; an enclosed Carbide Nomad 3 CNC. Reuses the existing blue pegboard benches + cabinetry.

### Engineering · Rm 305 + 310

≥4 Bambu Lab printers: H2D large-format + X1E enterprise + 3× P1S + AMS, enclosures, filament. Repurpose the existing NVIDIA-GPU tower desktops in 310 for AI hosting (10GbE NICs, RAM, IP-KVM) — engineering compute for near-zero new spend.

| Division | Representative real SKUs (June 2026) | Planning range |
| --- | --- | --- |
| AI Studio compute (lean) | Framework Desktop 128GB · Mac Studio M4 Max 64GB · DGX Spark · RTX 5090 WS · Jetson Thor/Orin · Synology DS1825+ · rack UPS | $30,000–$33,000 |
| Engineering Bambu fleet + GPU repurposing | Bambu H2D AMS Combo ~$2,199 · X1E ~$2,649 · 3× P1S+AMS ~$799 · BOFA PrintPRO 3 · Intel X550-T2 NICs · PiKVM V4 | $16,900–$18,500 |
| Soldering bench + CNC | 5–10× Hakko FX-888DX (~$135) · bench fume extraction · Carbide Nomad 3 ~$2,800 | $8,000–$9,000 |
| AV: 3 hallway display boards + 85″ studio demo wall | 3× ~50″ commercial displays + UniFi Connect signage/media players + mounts · 85″ demo wall ~$4,600 | $8,250–$9,120 |
| Furniture (movable) · Consumables/safety · Software/warranty | Movable benches/chairs · filament/resin/PPE/flammables cabinet/ABC+Class-D extinguishers · licenses + extended warranty | $9,800–$11,900 |
| Quote 1 grant-eligible subtotal (equipment + supplies) |  | $88,242–$98,820 |

Display / project boards (your spec): a board outside each of the three labs (409 / 407 / 305-310), auto-fed from in-room activity via UniFi Connect — "you see AI happening before you enter the room." The 85″ demo wall + per-semester access make the studio look intentional and impressive. Grant tag: items ≥$2,000/unit are EQUIPMENT; the many <$2,000 items are SUPPLIES — confirm with the grants officer whether rack components aggregate to a capitalized system.

Island Dev Crew Consulting · jon-isaac@islanddevcrew.comOakwood AI Lab Proposal · Page 6 of 13

## 9 · Quote 2 — Power / Electrical (Facility · NOT grant · subbed + GC-managed)

| Scope (lab-focused) | Planning range |
| --- | --- |
| Replace the FPE panel · 100A lab subpanel · 14 dedicated 20A circuits · 2× 30A L5-30 UPS circuits · conduit/raceway on cinderblock · lab touch-ups · permits | $34,000–$37,000 |

Load calc (electrician verifies): ~7–9kW continuous / ~12kW peak (~60–75A @120V) → a dedicated 100A subpanel is the floor (NEC 125% continuous derating; resolve 120/240V vs 208V; size the CNC circuit for inrush). The Federal Pacific panel (EX-01–03) should be replaced regardless of the AI build — a standalone life-safety item. Named Huntsville subs to bid: Madison Electric, Pro Electric, Lee Company, Blake Brothers, Urban Electric.

## 10 · Quote 3 — Network + Wi-Fi + Cameras + Access (Mixed: electronics grant / cabling facility)

| Division | Real SKUs (June 2026) | Range | Lane |
| --- | --- | --- | --- |
| UniFi core + pfSense | UniFi EnterpriseXG-24 ($1,299) · 2× USW-Pro-Max-24-PoE ($799) · UDM-Pro-Max ($599) · Netgate 6100 MAX pfSense ($999) · 42U rack | $3,837–$4,500 | Grant |
| UniFi Protect cameras | UNVR-Pro ($499) + 8TB HDDs · 10–12× G5/G6 Turret/Bullet ($129–$199) · AI Pro ($499) for the print room | $3,055–$3,800 | Grant |
| UniFi Access — 4 doors, rotating credentials | 4–5× UA-Hub-Door ($199) · G3 Reader Pro ($379) + G3 Readers ($159) · fail-safe HES strikes/maglock + REX + DPS + install | $8,400–$9,000 | Equip+install |
| Structured cabling — lab-focused (SUBBED) | Cat6A drops + patch panel + MDF rack rebuild (cabling labor = facility) | $12,000–$14,000 | Facility |

Per-semester rotating credentials are native to UniFi Access (PIN expiry, NFC deactivation, mobile/Wallet revoke). Named Huntsville subs: low-voltage — Travel Tech (256.970.4558), Interweave (256-837-2300), Heart Technologies (256-859-4000), State Systems; access — AAC Systems, Clear Link, LOCKTEC (256-881-9300), Tri-State Electrical. ADA/egress: all locks fail-safe; maglocks tie to the fire panel with REX + push-to-exit; Huntsville AHJ sign-off; low-voltage permit carried in Permits.

Island Dev Crew Consulting · jon-isaac@islanddevcrew.comOakwood AI Lab Proposal · Page 7 of 13

## 11 · Execute-Ready Invoice — Recommended Execution

Invoice basis: IDC (Jonathan Isaac) as General Contractor. Grant-eligible lines may be procured under Title III; facility lines are subbed and carry GC coordination. Re-quote each line to a sealed bid before purchase.

| # | Line item | Amount (range) |
| --- | --- | --- |
| I · Grant-Eligible Equipment & Supplies (Title III) |  |  |
| 1 | AI Studio compute — studio/lean tier | $30,000–$33,000 |
| 2 | Engineering Bambu fleet + GPU-PC repurposing | $16,900–$18,500 |
| 3 | Soldering bench + CNC | $8,000–$9,000 |
| 4 | Consumables / safety / storage | $3,000–$3,800 |
| 5 | AV — 3 hallway display boards + 85″ studio demo wall | $8,250–$9,120 |
| 6 | UniFi network core + pfSense edge | $3,837–$4,500 |
| 7 | UniFi Protect cameras — priority labs + key hallway | $3,055–$3,800 |
| 8 | UniFi Access — 4 doors, per-semester rotating credentials | $8,400–$9,000 |
| 9 | Furniture (movable lab/studio) | $5,000–$5,800 |
| 10 | Software / licensing / extended warranty | $1,800–$2,300 |
| Grant-eligible subtotal |  | $88,242–$98,820 |
| II · Facility — Capital / Donor (NOT grant-eligible · SUBBED) |  |  |
| 11 | Power / electrical — FPE replacement, subpanel, circuits, raceway, permits | $34,000–$37,000 |
| 12 | Structured cabling — lab-focused (Cat6A drops, patch, MDF rebuild) | $12,000–$14,000 |
| 13 | Raised access floor — AI Studio only (~300–400 sqft) + light room mod | $8,000–$10,000 |
| 14 | Permits / insurance / freight | $2,400–$2,800 |
| Facility subtotal |  | $56,400–$63,800 |
| Direct cost (I + II) |  | $144,642–$162,620 |
| III · GC Coordination, Contingency & IDC Fee |  |  |
| 15 | GC coordination markup — 3–7% on the subbed facility base only | $1,692–$4,466 |
| 16 | Contingency — 6–8% on (direct + markup); 2026 memory-price volatility | $8,780–$13,367 |
| 17 | IDC Orchestration Fee — 10% of pre-fee subtotal | $15,511–$18,045 |
| ALL-IN TOTAL · Recommended commitment $172,000 |  | $170,625–$198,498 |

### Payment schedule (proposed)

- $68,000 mobilization — on signature; initiates procurement & sub scheduling.

- ~50% progress — at equipment delivery + electrical/cabling rough-in.

- Balance at completion — commissioning, demo day, & closeout docs.

Pay deposit: IDC Stripe payment link ($68,000)

### Acceptance & signatures

Signature-ready; DocuSign / SignWell / Adobe / print-scan accepted.

Provider

Jonathan Isaac
Island Development Crew LLC
jon-isaac@islanddevcrew.com

Signature / Date

Client

Dr. Shushannah Smith
Oakwood University · Math & CS
ssmith@oakwood.edu

Signature / Date

Island Dev Crew Consulting · jon-isaac@islanddevcrew.comOakwood AI Lab Invoice · Page 8 of 13

## 12 · Curriculum Spine — 2084 / John Lennox (responsible-AI ethics for an Adventist HBCU)

Textbook: "2084 and the AI Revolution" (Updated & Expanded Ed., John C. Lennox, Zondervan Reflective 2024). The class meets twice weekly (e.g., Mon/Wed or Tue/Thu); one chapter is discussed per session — ~2 chapters/week, so the cohort reads through the whole book over the term while every 1–2 weeks ships one of 8 portfolio products. Two interleaved courses (AI Engineering + hands-on Machining/CNC) share this one ethics seminar. Pricing & outcomes on p.10.

| Wk | Ethics seminar — Lennox (≈2 ch/wk) | AI Engineering room (Rm 409 / 310) + fabrication (407 / 305) | Product shipped |
| --- | --- | --- | --- |
| 1 | Ch 1–2 · Mapping AI + where we come from | Onboarding · Python/Git · first local LLM on the Rm 310 GPUs; local-vs-cloud | — setup |
| 2 | Ch 3–4 · Trajectory / surveillance + narrow-AI promise | Build a RAG assistant on a local model; prompt & retrieval basics | P1 Local RAG assistant |
| 3 | Ch 5–6 · Narrow-AI harms & bias + upgrading humans | CV classifier + bias/fairness audit; model cards | P2 CV model + bias audit |
| 4 | Ch 7–8 · AGI risk + what is a human being | Agentic workflow (tool-use) + guardrails; prompt-injection red-team | — |
| 5 | Ch 9–10 · Origin of moral sense + the true Homo Deus | Voice/assistive-tech device — AI + a 3D-printed part on the Bambu fleet | P3 Assistive-tech AI device |
| 6 | Ch 11–12 · Future shock / revelation | Multimodal app; deploy to Vercel with a Supabase backend | P4 Deployed multimodal app |
| 7 | Ch 13 + synthesis · responsible AI & the time of the end | Eval harness + red-team; responsible-AI governance memo; demo-board publish | P5 Eval + governance memo |
| 8 | Applied sprint · ethics review embedded in code review | Business / SaaS build: auth, database, billing | P6 SaaS product |
| 9 | Applied sprint | Agentic product via OpenRouter multi-model routing (local + frontier) | — |
| 10 | Publication / research artifact | Technical write-up + research poster; hallway demo board | P7 Publication / poster |
| 11 | Capstone build | Ship a real campus tool (à la the OU Campus Companion) | — |
| 12 | Capstone demo day | Polish + portfolio site; present the 8-product portfolio | P8 Capstone + portfolio |

Reading completes the core 2084 arc by ~week 7; weeks 8–12 are build sprints with the ethics lens carried into every code review. The fabrication track (soldering / 3D-print / CNC) runs in parallel so several of the 8 products are physical-AI devices, not just software.

Island Dev Crew Consulting · jon-isaac@islanddevcrew.comOakwood AI Lab Proposal · Page 9 of 13

## 13 · Curriculum — Per-Student Toolchain, Pricing & Outcomes

### Per-student digital toolchain (~$200–$250 / semester)

| Tool | / mo | What it unlocks |
| --- | --- | --- |
| ChatGPT Plus | $20 | OpenAI frontier models |
| Claude Pro | $20 | Anthropic frontier models |
| Google Gemini | $20 | Google frontier models |
| xAI Grok | $20 | xAI frontier models |
| OpenRouter credit | $20 | One API → local, Chinese & all frontier models |
| Vercel | ~$0–20 | Ship/host student apps |
| Supabase | ~$0–25 | Auth + database backend |
| ≈ $100/mo subscriptions + hosting |  | = $200–$250 / student for the semester |

This gives every student the top four frontier labs + local & open models via one toolchain — enough to design, build, deploy, and host real products.

### All-in student price & the outcome

- All-in: $300–$350 / student — the $200–$250 digital toolchain + course materials + the 2084 book (combined; no separate book charge).

- The deliverable: by the time they leave the class — and certainly by graduation — each student has 8 fully functioning products to their name: an app, a business, software, a physical-AI device, or a publication.

- The promise: students graduate job-ready and able to ship — a sharpened, market-relevant portfolio instead of just a résumé.

### Why it lands at Oakwood

As the only SDA HBCU, Oakwood can teach AI with a worldview-grounded ethics voice secular schools struggle to articulate — data dignity, human-in-the-loop, Sabbath as a model for digital rest. Graduates leave with a portfolio and a point of view.

Island Dev Crew Consulting · jon-isaac@islanddevcrew.comOakwood AI Lab Proposal · Page 10 of 13

## 14 · Fundraising, Match Funds & the Naming Opportunity

### Grant & corporate funding

- Federal HBCU + AI: NSF ExpandAI, NSF HBCU-EiR, NSF HBCU-UP, Dept of Ed Title III Part B (Oakwood is an active recipient).

- Compute/hardware programs: NVIDIA Academic Grant, AMD University Program, Google.org / UNCF.

- Mission-fit philanthropy: John Templeton Foundation, Lilly Endowment (faith & AI), Mellon ("Unruly Intelligences").

- Corporate matching-gift programs.

### Notoriety & the naming track

- Voices to engage: Dr. James Tour, John Lennox, Wesley Huff — credible on AI + faith + science.

- Channels: Modern Wisdom, Valuetainment, Diary of a CEO — to spotlight an HBCU building responsible AI.

- Naming opportunity: "The John Lennox AI Innovation Lab" (pending Oakwood approval) — pairs the 2084 curriculum with a named-gift envelope that funds the grant-ineligible facility scope.

## 15 · Department-Wide Vision (donor / naming ask · $245K–$330K)

| Division (full scope) | Range | Division (full scope) | Range |
| --- | --- | --- | --- |
| AI Studio compute (pooled · RTX PRO 6000) | $42K–$50K | Power / electrical (full dept) | $34K–$48K |
| Engineering Bambu fleet (full) | $20K–$23.9K | Structured cabling (80 drops + fiber) | $24K–$36K |
| Soldering + CNC (full) | $11K–$14K | Raised floor + Room-405 bathroom + room mod | $45.6K–$62K |
| Cameras (dept-wide) + Access (5 doors) | $15K–$19K | Network core, AV, furniture, software, permits | $24K–$30K |
| Department-Wide Vision — all-in (incl. GC markup + 10% IDC fee) |  |  | $245,000–$330,000 |

Island Dev Crew Consulting · jon-isaac@islanddevcrew.comOakwood AI Lab Proposal · Page 11 of 13

## 16 · Primary Source Links & References

Every quoted price traces to a named vendor or published benchmark (current June 2026). Re-quote each line to a sealed bid before purchase; 2026 memory-market pricing is time-sensitive.

### AI / Compute

- Oakwood AI Lab — final web reference

- NVIDIA DGX Spark — marketplace

- NVIDIA DGX Spark — product

- Framework Desktop

- Apple Education Institution Price List

- NVIDIA Jetson Orin Nano Super

- NVIDIA Jetson AGX Thor

- Synology DiskStation

### Engineering / Fabrication

- Bambu Lab P1S

- Bambu Lab H2D (large format)

- Bambu Lab X1E (enterprise)

- Original Prusa XL

- Hakko FX-888DX soldering station

- Hakko fume extraction

- Donaldson BOFA 3D PrintPRO

- Carbide 3D Nomad 3 CNC

### Network / Security

- Ubiquiti UniFi store

- UniFi U7 Pro Max AP

- UniFi EnterpriseXG-24 (10GbE core)

- UniFi Dream Machine Pro Max

- Netgate 6100 MAX (pfSense+)

- UniFi Protect cameras

- UniFi Access (door control)

### Student toolchain / curriculum

- ChatGPT (OpenAI)

- Claude (Anthropic)

- Google Gemini

- xAI Grok

- OpenRouter (one API, all models)

- Vercel (hosting)

- Supabase (backend/DB)

- 2084 and the AI Revolution (Lennox, 2024)

### Facility benchmarks

- Ethernet / structured cabling install cost

- Dedicated circuit install cost

- Raised access floor cost guide

### Named Huntsville subcontractors (for the facility scope)

| Trade | Named Huntsville-area subcontractors (solicit 3 sealed bids each) |
| --- | --- |
| Electrical | Madison Electric Inc · Pro Electric Inc · Lee Company · Blake Brothers · Urban Electric LLC |
| Low-voltage / cabling | Travel Tech (256.970.4558) · Interweave Technologies (256-837-2300) · Heart Technologies (256-859-4000) · State Systems Inc. |
| Access control / locks | AAC Systems LLC · Clear Link Systems · LOCKTEC Inc. (256-881-9300) · Tri-State Electrical Contractors |
| General contracting / raised floor | Regional Builders (256-684-8833) · Wilcock Builders · Lee Builders · Pro Access Floors · Southwest Solutions Group · Intertech Commercial Flooring |

Full audited bill of materials with per-line SKUs and source URLs is in the package price book; all 71 walkthrough photographs at full resolution with explanations are on the online resource page.

Island Dev Crew Consulting · jon-isaac@islanddevcrew.comOakwood AI Lab Proposal · Page 12 of 13

## 17 · Orchestration, Reporting & Next Steps

### Single point of accountability

IDC engages and schedules every vendor & Huntsville sub, manages the grant vs. facility funding lanes, and owns the timeline. One markup, one fee, one invoice.

### Live progress & reporting

A live HTML progress dashboard link is attached to the project email; weekly & monthly progress reports keep faculty & administration abreast through commissioning.

### Protected investment

Department cameras + per-semester rotating access control + cabling/power done to code (incl. FPE panel replacement) mean the equipment is controlled, managed, and protected from day one.

## Open items to confirm before sealed bids

- Final room dimensions & seat count (Rm 409 measured pass) — required for the raised-floor quote.

- Campus-IT vendor ruling: UniFi/pfSense allowed, or map to Aruba/Cisco/Extreme? Does access tie to the campus card?

- Oakwood tax-exempt status + grant eligibility ruling (setup labor, software/SaaS, networking hardware, cabling labor, access hardware).

- Tier to commit: Recommended ~$172K vs. a sub-$170K trim (single-lab cameras / 2-door access).

Recommended next step. Approve the Recommended Execution tier (~$172,000 all-in), release the $68,000 mobilization deposit (Stripe link, p.1 / p.8), and authorize IDC to (1) commission the licensed-electrician load study and (2) issue three sealed sub bids per trade. IDC returns firm, signed numbers within ~10 business days and begins the 90-day build.

Online: Package hub · All 71 photos + references · Live dashboard · Pay $68K deposit

Authorized to proceed — Provider

Jonathan Isaac · Island Development Crew LLC

Signature / Date

Authorized to proceed — Client

Dr. Shushannah Smith · Oakwood University

Signature / Date

Island Dev Crew Consulting · jon-isaac@islanddevcrew.comOakwood AI Lab Proposal · Page 13 of 13